# CyberRisk Monitor

A Lightweight Rule-Based Cybersecurity Monitoring and Risk Assessment Tool

UMGC CMSC 495 - Computer Science Capstone

Project Design Document

Spring 2026

Team Members:

Mustafa Black-Castle, Daniel S. Garrett, Nicholas Porpora, and Cassandra Santacruz

# Table of Contents

1. Introduction

2. Project Scope

3. Project Requirements

4. Project Methodology

5. Work Breakdown Structure and Project Tasks

6. Project Schedule

7. Project Resources

8. Project Risks

9. Project Evaluation Plan

10. System Design

11. Testing and Validation Strategy

12. Conclusion

Appendix A: Detailed Class Specifications

Appendix B: Detection Rules Catalog

# 1. Introduction

This Project Design document presents the execution roadmap for CyberRisk Monitor, a lightweight rule-based cybersecurity monitoring and risk assessment tool developed as part of the UMGC CMSC 495 Computer Science Capstone. The purpose of this document is to translate the approved Project Plan into a structured design and implementation strategy that guides development, scheduling, risk management, and evaluation activities throughout the project lifecycle.

CyberRisk Monitor is designed as a proof-of-concept system rather than a full-scale enterprise solution. The project focuses on analyzing simulated or sample security logs using predefined detection rules to identify indicators of suspicious or potentially malicious activity. The system emphasizes clarity, interpretability, and accessibility, making it suitable for educational environments and small teams seeking an introductory cybersecurity monitoring capability.

This document builds upon the previously established Project Plan by expanding on technical requirements, task decomposition, scheduling logic, and evaluation criteria. It serves as a comprehensive reference for how the project will be executed, monitored, and assessed to ensure alignment with course objectives and successful capstone delivery.

## 1.1 Document Purpose

This design document serves multiple purposes:

Provide a detailed roadmap for project execution from Week 3 through Week 8

Define clear scope boundaries, deliverables, and success criteria

Establish a structured work breakdown with accurate time and resource estimates

Identify and analyze potential risks with corresponding mitigation strategies

Create measurable evaluation criteria aligned with project objectives

Guide the development team through a systematic implementation process

## 1.2 Intended Audience

This document is intended for course instructors evaluating the project plan, team members executing the development work, and any stakeholders interested in understanding the project's scope and approach.

# 2. Project Scope

The scope of the CyberRisk Monitor project defines the objectives, deliverables, boundaries, and limitations necessary to ensure successful completion within the fixed academic timeline of the capstone course.

## 2.1 Project Objectives

The primary objective is to design, implement, and deliver a functional cybersecurity monitoring tool capable of analyzing structured log data and identifying indicators of suspicious or potentially malicious activity using predefined detection rules. The following specific objectives guide the project:

| Objective ID | Objective Description | Success Criteria |
| --- | --- | --- |
| OBJ-01 | Develop a log parsing system supporting multiple formats | Successfully parse syslog, JSON, and CSV formats with >95% accuracy |
| OBJ-02 | Implement rule-based detection engine | Execute 10-15 detection rules with correct pattern matching |
| OBJ-03 | Create risk scoring and categorization system | Accurately categorize events into Low/Medium/High/Critical levels |
| OBJ-04 | Build user-friendly reporting interface | Generate clear summary reports and visualizations |
| OBJ-05 | Deliver documented, maintainable codebase | Complete documentation with >80% code coverage in tests |

Table 2.1: Project Objectives and Success Criteria

## 2.2 Project Deliverables

The following deliverables will be produced upon project completion:

Functional CyberRisk Monitor application with all core modules

LogParser module supporting syslog, JSON, and CSV formats

RuleEngine module with 10-15 predefined detection rules

RiskScorer module with configurable scoring algorithms

ReportGenerator module producing summary reports and visualizations

UserInterface providing command-line and/or graphical interaction

Sample log datasets for testing and demonstration

Comprehensive code documentation and user manual

Final project presentation and demonstration materials

## 2.3 Scope Boundaries

The following table clearly defines what is included and excluded from this project:

| In Scope | Out of Scope |
| --- | --- |
| Analysis of simulated/sample security log data | Real-time monitoring of live network traffic |
| Implementation of 10-15 predefined detection rules | Integration with production/enterprise environments |
| Basic risk scoring and categorization (Low/Medium/High/Critical) | Machine learning or AI-based detection techniques |
| Summary dashboards and structured reports | Automated incident response or remediation |
| Support for syslog, JSON, and CSV formats | Enterprise-scale log aggregation or storage |
| Command-line and/or simple graphical interface | Regulatory compliance frameworks (HIPAA, PCI-DSS) |
| Offline batch processing of log files | Network packet capture or deep packet inspection |

Table 2.2: Project Scope Boundaries

## 2.4 Constraints and Limitations

| Constraint Type | Description |
| --- | --- |
| Time Constraint | Project must be completed within 6 weeks (Weeks 3-8 of the course) |
| Team Size | Limited to 4 team members with varying availability |
| Budget | Zero budget; all tools and resources must be free or open-source |
| Technical | Cross-platform compatibility required (Windows, macOS, Linux) |
| Data | Must use simulated/sample data only; no access to real security logs |
| Complexity | Proof-of-concept level; not production-ready enterprise software |

Table 2.3: Project Constraints and Limitations

## 2.5 Assumptions

All team members have access to suitable development environments

Team members possess foundational Python programming skills

Adequate sample log data is available or can be generated for testing

Team members can dedicate approximately 8-12 hours per week to the project

Git/GitHub is accessible for version control and collaboration

Internet access is available for research and tool downloads

# 3. Project Requirements

Project requirements for CyberRisk Monitor were derived from capstone course objectives, foundational cybersecurity practices, and the intended educational use of the system. These requirements ensure that the project demonstrates essential monitoring and risk assessment capabilities while remaining achievable within time and resource constraints.

## 3.1 User Needs Analysis

The target users of CyberRisk Monitor are students, educators, and small teams who need an accessible introduction to cybersecurity monitoring concepts. User needs include:

| User Need | Description |
| --- | --- |
| Transparency | Users need to understand why alerts are generated and how risk scores are calculated |
| Simplicity | Users require an intuitive interface that does not require extensive cybersecurity expertise |
| Education | Users benefit from clear explanations of detected security patterns |
| Flexibility | Users need the ability to adjust detection thresholds based on their environment |
| Accessibility | Users require cross-platform support and minimal installation complexity |

Table 3.1: User Needs Analysis

## 3.2 Functional Requirements

Functional requirements define the specific behaviors and capabilities the system must exhibit:

| Req ID | Requirement Description | Priority | Verification Method |
| --- | --- | --- | --- |
| FR-01 | The system shall parse security logs in syslog-style text, JSON, and CSV formats | High | Unit Testing |
| FR-02 | The system shall apply predefined and configurable detection rules to parsed log data | High | Integration Testing |
| FR-03 | The system shall identify common security patterns (failed logins, port scanning, privilege escalation) | High | Functional Testing |
| FR-04 | The system shall calculate numerical risk scores for detected events | High | Unit Testing |
| FR-05 | The system shall categorize detected risks as Low, Medium, High, or Critical | High | Validation Testing |
| FR-06 | The system shall generate summary reports of detected findings | Medium | Functional Testing |
| FR-07 | The system shall present results through a dashboard or structured report interface | Medium | User Acceptance |
| FR-08 | The system shall allow users to adjust detection rule thresholds | Low | Configuration Testing |

Table 3.2: Functional Requirements

## 3.3 Non-Functional Requirements

Non-functional requirements define the quality attributes and constraints on system behavior:

| Req ID | Requirement Description | Category | Acceptance Criteria |
| --- | --- | --- | --- |
| NFR-01 | Process up to 10,000 log entries within 30 seconds on standard hardware | Performance | Benchmark testing shows <30s processing time |
| NFR-02 | User interface understandable for users with basic technical knowledge | Usability | User can perform analysis without documentation |
| NFR-03 | Include error handling and internal logging for debugging | Reliability | No unhandled exceptions; errors logged |
| NFR-04 | Codebase documented and follows consistent coding standards | Maintainability | Code review approval; docstrings present |
| NFR-05 | Cross-platform compatibility (Windows, macOS, Linux) | Portability | Successful execution on all three platforms |
| NFR-06 | Modular architecture supporting future enhancements | Extensibility | Clear separation of concerns in design |

Table 3.3: Non-Functional Requirements

## 3.4 Technical Requirements

| Component | Specification |
| --- | --- |
| Programming Language | Python 3.10 or later |
| Operating System | Cross-platform (Windows, macOS, Linux) |
| Version Control | Git with shared GitHub repository |
| Core Libraries | Standard Python libraries (json, csv, re, datetime, logging) |
| Optional Frameworks | Flask or Streamlit for web-based visualization |
| Configuration Format | JSON or YAML files for rules and settings |
| Data Storage | File-based; optional SQLite for persistence |
| Testing Framework | pytest for unit and integration testing |

Table 3.4: Technical Requirements

# 4. Project Methodology

## 4.1 Methodology Selection: Agile-Inspired Iterative Development

The CyberRisk Monitor project follows an Agile-inspired iterative development methodology adapted to the structure of the CMSC 495 capstone course. This approach organizes development activities into short, iterative cycles aligned with weekly course milestones, allowing for incremental progress and regular reassessment of project status.

## 4.2 Justification for Methodology Selection

The Agile-inspired approach was selected based on the following project characteristics:

| Project Characteristic | How Agile Addresses It |
| --- | --- |
| Fixed Timeline | Weekly iterations ensure continuous progress within the 6-week constraint |
| Small Team | 4-person team benefits from lightweight processes over heavy documentation |
| Educational Context | Iterative demos allow instructor feedback and course alignment |
| Technical Uncertainty | Flexibility to adapt as team learns cybersecurity concepts |
| Integration Complexity | Early and continuous integration reduces end-of-project risk |
| Deliverable Focus | Each iteration produces working software demonstrating progress |

Table 4.1: Methodology Justification

## 4.3 Iteration Structure

Each weekly iteration follows a structured pattern that balances development work with team coordination and quality assurance:

Planning (Monday): Review tasks for the week, assign responsibilities, identify blockers

Development (Monday-Friday): Execute assigned tasks, implement features, write tests

Integration (Thursday): Merge code, resolve conflicts, verify component compatibility

Testing (Thursday-Friday): Run unit tests, integration tests, and manual verification

Review (Friday): Team meeting to demonstrate progress, discuss issues, plan next iteration

Documentation (Ongoing): Update code comments, maintain user documentation

## 4.4 Communication and Collaboration

The team employs the following communication practices:

Weekly team meetings (virtual) for planning and review

Shared GitHub repository for code collaboration and version control

Issue tracking via GitHub Issues for task management

Direct messaging (Discord/Slack) for quick questions and coordination

Shared documentation repository for design documents and notes

## 4.5 Comparison with Waterfall Approach

A traditional Waterfall approach was considered but rejected due to its limitations in this context. The following table compares both approaches:

| Aspect | Waterfall | Agile (Selected) |
| --- | --- | --- |
| Feedback Timing | Late (after full implementation) | Continuous (each iteration) |
| Risk of Failure | High (issues found late) | Low (issues found early) |
| Flexibility | Low (changes are costly) | High (changes are expected) |
| Progress Visibility | Limited until end | Demonstrated weekly |

Table 4.2: Methodology Comparison

# 5. Work Breakdown Structure and Project Tasks

The project work is decomposed into manageable tasks organized by development phase and functional responsibility. This work breakdown structure supports parallel development while maintaining clear dependencies between system components.

## 5.1 Work Breakdown Structure Diagram

The following diagram illustrates the hierarchical decomposition of project work:

Figure 5.1: Work Breakdown Structure (WBS) Diagram

## 5.2 Task Breakdown by Phase

### Phase 1: Planning and Design (Week 3)

| Task ID | Task Description | Owner | Est. Hours | Deliverable |
| --- | --- | --- | --- | --- |
| T1.1 | Finalize requirements documentation | Mustafa | 6 | Requirements Document |
| T1.2 | Design system architecture | Nicholas | 8 | Architecture Diagram |
| T1.3 | Define detection rules catalog | Daniel | 6 | Rules Specification |
| T1.4 | Set up development environment | All | 4 | Working Dev Environment |

### Phase 2: Core Development I (Week 4)

| Task ID | Task Description | Owner | Est. Hours | Deliverable |
| --- | --- | --- | --- | --- |
| T2.1 | Implement LogParser base module | Daniel | 10 | LogParser.py |
| T2.2 | Implement syslog format handler | Daniel | 6 | Syslog parser |
| T2.3 | Implement JSON/CSV format handlers | Daniel | 6 | JSON/CSV parsers |
| T2.4 | Create unit tests for parsing | Daniel | 4 | test_logparser.py |

### Phase 3: Core Development II (Week 5)

| Task ID | Task Description | Owner | Est. Hours | Deliverable |
| --- | --- | --- | --- | --- |
| T3.1 | Implement RuleEngine module | Mustafa | 12 | RuleEngine.py |
| T3.2 | Implement RiskScorer module | Nicholas | 10 | RiskScorer.py |
| T3.3 | Create detection rules (10-15 rules) | Mustafa | 8 | rules_config.json |
| T3.4 | Unit tests for rules and scoring | Nicholas | 6 | test_rules.py |

### Phase 4: Integration (Week 6)

| Task ID | Task Description | Owner | Est. Hours | Deliverable |
| --- | --- | --- | --- | --- |
| T4.1 | Integrate LogParser with RuleEngine | Nicholas | 6 | Integrated pipeline |
| T4.2 | Integrate RiskScorer with pipeline | Nicholas | 6 | Full analysis chain |
| T4.3 | Implement ReportGenerator module | Cassandra | 10 | ReportGenerator.py |
| T4.4 | Integration testing | All | 8 | Integration test suite |

### Phase 5: UI and Testing (Week 7)

| Task ID | Task Description | Owner | Est. Hours | Deliverable |
| --- | --- | --- | --- | --- |
| T5.1 | Implement UserInterface (CLI) | Cassandra | 8 | cli.py |
| T5.2 | Implement dashboard visualization | Cassandra | 10 | Dashboard module |
| T5.3 | System testing and bug fixes | All | 10 | Test reports |
| T5.4 | Performance optimization | Mustafa | 4 | Optimized code |

### Phase 6: Final Delivery (Week 8)

| Task ID | Task Description | Owner | Est. Hours | Deliverable |
| --- | --- | --- | --- | --- |
| T6.1 | Finalize code documentation | All | 6 | Documented codebase |
| T6.2 | Create user manual | Cassandra | 6 | User Manual |
| T6.3 | Performance validation | Daniel | 4 | Benchmark results |
| T6.4 | Prepare final demonstration | Mustafa | 6 | Demo presentation |

## 5.3 Task Dependencies

The following critical dependencies exist between tasks:

T2.1-T2.4 (LogParser) must complete before T4.1 (Integration with RuleEngine)

T3.1 (RuleEngine) must complete before T4.1 (Integration)

T3.2 (RiskScorer) must complete before T4.2 (Pipeline Integration)

T4.1-T4.2 (Integration) must complete before T5.1-T5.2 (UI Development)

T4.3 (ReportGenerator) must complete before T5.2 (Dashboard)

All development tasks must complete before T6.3 (Performance Validation)

T6.1-T6.3 must complete before T6.4 (Final Demonstration)

## 5.4 Total Effort Summary

| Phase | Total Hours | Team Members Involved |
| --- | --- | --- |
| Phase 1: Planning & Design | 24 | All (6 hrs each) |
| Phase 2: Core Development I | 26 | Daniel (primary) |
| Phase 3: Core Development II | 36 | Mustafa, Nicholas |
| Phase 4: Integration | 30 | Nicholas, Cassandra |
| Phase 5: UI & Testing | 32 | Cassandra, All |
| Phase 6: Final Delivery | 22 | All |
| TOTAL | 170 | ~42.5 hrs per member |

Table 5.1: Total Effort Summary by Phase

# 6. Project Schedule

The project schedule spans six weeks, corresponding to Weeks 3 through 8 of the capstone course. Milestones are structured to ensure consistent progress while allocating sufficient time for integration, testing, and refinement.

## 6.1 Project Timeline (Gantt Chart)

The following Gantt chart illustrates the project timeline with task durations, dependencies, and milestones:

Figure 6.1: Project Schedule Gantt Chart

## 6.2 Milestones and Deadlines

| Milestone | Target Date | Deliverables | Success Criteria |
| --- | --- | --- | --- |
| M1: Design Complete | End of Week 3 | Design document, Architecture diagram | Approved by team lead |
| M2: Parser Ready | End of Week 4 | LogParser module, Unit tests | All format handlers tested |
| M3: Core Engine Ready | End of Week 5 | RuleEngine, RiskScorer modules | Rules execute correctly |
| M4: Integration Complete | End of Week 6 | Integrated pipeline, ReportGenerator | End-to-end test passes |
| M5: UI Complete | End of Week 7 | UserInterface, Dashboard | User can run full analysis |
| M6: Project Delivery | End of Week 8 | Final code, Documentation, Demo | All requirements met |

Table 6.1: Project Milestones and Deadlines

## 6.3 Weekly Schedule Detail

| Week | Primary Focus | Key Activities |
| --- | --- | --- |
| Week 3 | Planning & Design | Requirements finalization, Architecture design, Rule definition, Environment setup |
| Week 4 | Core Development I | LogParser implementation, Format handlers (syslog, JSON, CSV), Unit testing |
| Week 5 | Core Development II | RuleEngine implementation, RiskScorer implementation, Detection rules creation |
| Week 6 | Integration | Component integration, ReportGenerator development, Integration testing |
| Week 7 | UI & Testing | CLI and Dashboard development, System testing, Performance optimization |
| Week 8 | Final Delivery | Documentation, Performance validation, Demo preparation, Final submission |

Table 6.2: Weekly Schedule Detail

## 6.4 Critical Path

The critical path for this project runs through the following sequence of dependent tasks:

Critical Path: Requirements Analysis (Week 3) -> LogParser Module (Week 4) -> RuleEngine Module (Week 5) -> Component Integration (Week 6) -> UserInterface Development (Week 7) -> Final Demo Preparation (Week 8)

Any delays in these tasks will directly impact the final delivery date. Buffer time has been allocated within each phase to absorb minor delays without affecting subsequent milestones.

# 7. Project Resources

This section identifies and allocates the personnel, equipment, and budget resources required for successful project completion.

## 7.1 Team Member Allocation

| Team Member | Role | Primary Responsibilities | Availability | Est. Hours |
| --- | --- | --- | --- | --- |
| Mustafa Black-Castle | Project Lead | RuleEngine, Coordination, Demo | 10-12 hrs/week | 40 |
| Daniel S. Garrett | Lead Developer | LogParser, Testing Lead | 10-12 hrs/week | 40 |
| Nicholas Porpora | Developer | RiskScorer, Integration | 10-12 hrs/week | 40 |
| Cassandra Santacruz | Developer | UI, Documentation, Reports | 10-12 hrs/week | 40 |

Table 7.1: Team Member Allocation

## 7.2 Resource Allocation Visualization

Figure 7.1: Team Workload and Weekly Effort Distribution

## 7.3 Equipment and Software Resources

| Resource | Type | Cost | Availability |
| --- | --- | --- | --- |
| Personal Computers | Hardware | $0 (owned) | All team members |
| Python 3.10+ | Software | $0 (free) | Available |
| Git/GitHub | Version Control | $0 (free tier) | Available |
| VS Code/PyCharm | IDE | $0 (free editions) | Available |
| pytest | Testing Framework | $0 (open source) | Available |
| Streamlit/Flask | Web Framework | $0 (open source) | Available |
| Discord/Slack | Communication | $0 (free tier) | Available |
| Internet Access | Infrastructure | Personal expense | All team members |

Table 7.2: Equipment and Software Resources

## 7.4 Budget Summary

This project operates with a zero-dollar budget. All tools, frameworks, and resources utilized are free, open-source, or already owned by team members. The only implicit costs are team member time (estimated at 160 total person-hours) and personal internet access.

| Cost Category | Amount |
| --- | --- |
| Software Licenses | $0 |
| Hardware | $0 (existing equipment) |
| Cloud Services | $0 (not required) |
| TOTAL PROJECT BUDGET | $0 |

Table 7.3: Budget Summary

# 8. Project Risks

Cybersecurity projects often involve technical complexity and integration challenges, making proactive risk management essential. This section identifies potential risks, assesses their impact and likelihood, and outlines mitigation strategies.

## 8.1 Risk Assessment Matrix

The following matrix visualizes identified risks based on their likelihood and potential impact:

Figure 8.1: Risk Assessment Matrix

## 8.2 Risk Register

| Risk ID | Risk Description | Likelihood | Impact | Risk Level | Mitigation Strategy |
| --- | --- | --- | --- | --- | --- |
| R1 | Team member unavailability due to other commitments | Possible | Major | High | Cross-train on modules; maintain documentation; buffer time in schedule |
| R2 | Technical complexity exceeds team expertise | Unlikely | Moderate | Medium | Early research; leverage online resources; simplify scope if needed |
| R3 | Scope creep from feature requests | Possible | Moderate | Medium | Strict scope boundary enforcement; change control process |
| R4 | Integration issues between modules | Unlikely | Major | Medium | Define clear interfaces early; continuous integration testing |
| R5 | Learning curve for cybersecurity concepts | Possible | Minor | Medium | Early research; focus on educational resources; team knowledge sharing |
| R6 | Poor quality or insufficient test data | Rare | Moderate | Low | Create synthetic datasets early; validate data quality before testing |

Table 8.1: Risk Register

## 8.3 Detailed Mitigation Plans

### R1: Team Member Unavailability

Impact: Delays in task completion; potential knowledge gaps. Mitigation Actions:

Maintain comprehensive documentation for all modules

Ensure at least two team members understand each critical component

Hold weekly sync meetings to share progress and knowledge

Build buffer time into schedule for unexpected absences

Use GitHub Issues to track all tasks with clear descriptions

### R2: Technical Complexity

Impact: Extended development time; potential feature reduction. Mitigation Actions:

Conduct early research during Week 3 planning phase

Identify online tutorials and resources for unfamiliar concepts

Start with simple implementations and iterate

Seek instructor guidance when facing significant blockers

Be prepared to simplify scope while maintaining core functionality

### R3: Scope Creep

Impact: Delayed delivery; incomplete core features. Mitigation Actions:

Document clear scope boundaries in this design document

Require team consensus for any scope changes

Maintain a "future enhancements" list for ideas outside current scope

Prioritize core functionality over nice-to-have features

Review scope weekly during team meetings

### R4: Integration Issues

Impact: System fails to work as a cohesive unit. Mitigation Actions:

Define clear interfaces between modules during design phase

Use consistent data structures across all components

Implement continuous integration from Week 4 onwards

Write integration tests before full integration begins

Conduct code reviews to ensure interface compliance

## 8.4 Contingency Plans

| Scenario | Trigger Condition | Contingency Action |
| --- | --- | --- |
| Major delay (>1 week) | Milestone missed by >3 days | Reduce detection rules to 8; simplify UI to CLI only |
| Team member dropout | Member unavailable for >1 week | Redistribute tasks; focus on critical path items |
| Technical blocker | Issue unresolved for >3 days | Seek external help; simplify affected component |

Table 8.2: Contingency Plans

# 9. Project Evaluation Plan

Project success will be evaluated using both qualitative and quantitative criteria. This section establishes clear, measurable evaluation criteria aligned with project goals.

## 9.1 Evaluation Criteria

| Criterion | Metric | Target | Measurement Method |
| --- | --- | --- | --- |
| Functional Completeness | Requirements implemented | 100% of FR-01 to FR-08 | Requirements traceability matrix |
| Detection Accuracy | Rules correctly identify patterns | >90% true positive rate | Testing with known datasets |
| Performance | Log processing speed | <30 sec for 10,000 entries | Benchmark testing |
| Code Quality | Test coverage | >80% code coverage | pytest-cov report |
| Documentation | Completeness | All modules documented | Documentation review |
| Usability | User can complete analysis | Without documentation reference | User acceptance testing |
| Maintainability | Code follows standards | Passes linting checks | Automated code analysis |
| Milestone Adherence | On-time delivery | 100% milestones met | Schedule tracking |

Table 9.1: Evaluation Criteria and Metrics

## 9.2 Progress Monitoring

Progress will be monitored throughout the project using the following methods:

Weekly Status Reviews: Team meeting every Friday to assess progress against milestones

GitHub Metrics: Track commits, pull requests, and issue closure rates

Test Results: Monitor unit and integration test pass rates

Code Reviews: Peer review of all code before merging to main branch

Milestone Checkpoints: Formal review at each milestone completion

## 9.3 Quality Assurance Checkpoints

| Checkpoint | Week | Quality Gate Criteria |
| --- | --- | --- |
| Design Review | 3 | Architecture approved; requirements documented |
| Parser Quality Gate | 4 | All format tests pass; code reviewed |
| Engine Quality Gate | 5 | Detection rules validated; scoring correct |
| Integration Quality Gate | 6 | End-to-end test passes; no critical bugs |
| UI Quality Gate | 7 | User acceptance criteria met |
| Final Quality Gate | 8 | All criteria met; demo ready |

Table 9.2: Quality Assurance Checkpoints

## 9.4 Success Definition

The project will be considered successful if:

All functional requirements (FR-01 through FR-08) are implemented and working

The system can process 10,000 log entries within 30 seconds

At least 10 detection rules are implemented and validated

The user interface allows complete analysis workflow without errors

Code documentation covers all public interfaces

Final demonstration successfully shows all capabilities

All six milestones are completed by their target dates

## 9.5 Post-Project Evaluation

Following project completion, a retrospective evaluation will assess:

What worked well in the development process

What challenges were encountered and how they were addressed

Lessons learned for future projects

Potential improvements if the project were to continue

Team collaboration effectiveness

# 10. System Design

## 10.1 System Architecture Overview

CyberRisk Monitor follows a modular system architecture that separates data ingestion, rule evaluation, risk assessment, and presentation. This separation of concerns supports maintainability, testability, and clear responsibility boundaries.

Figure 10.1: System Architecture and Data Flow Diagram

## 10.2 Component Descriptions

LogParser: Ingests and normalizes log data from multiple input formats (syslog, JSON, CSV). Responsible for format detection, parsing, validation, and conversion to a unified internal representation.

RuleEngine: Applies detection rules to parsed log entries. Loads rule configurations, evaluates conditions against log data, and generates detection events for matching patterns.

RiskScorer: Calculates risk scores and assigns severity levels. Implements the scoring algorithm based on rule severity, event frequency, and contextual factors.

ReportGenerator: Produces summary reports and visualizations. Aggregates detection results, calculates statistics, and formats output for display or export.

UserInterface: Provides user interaction and output display. Supports command-line interface and optional graphical dashboard for analysis workflow.

## 10.3 UML Class Diagram

The following detailed UML class diagram illustrates the object-oriented design of the system:

Figure 10.2: Detailed UML Class Diagram

## 10.4 Original Conceptual Class Diagram

The following diagram shows the initial conceptual design that guided the detailed implementation:

Figure 10.3: Conceptual UML Class Diagram

## 10.5 Data Flow Description

The data flow within CyberRisk Monitor follows a deterministic and sequential processing model:

1. User selects one or more log files through the UserInterface

2. LogParser identifies the format of each input file and parses entries

3. Parsed entries are normalized into a unified LogEntry representation

4. RuleEngine evaluates each LogEntry against all active detection rules

5. Matching rules generate Detection events with associated metadata

6. RiskScorer calculates scores for each Detection based on severity and context

7. Detections are categorized into Low, Medium, High, or Critical severity levels

8. ReportGenerator aggregates results and generates summary statistics

9. UserInterface displays results through dashboard or exports reports

## 10.6 Rule Design

Detection rules are designed to identify common security patterns. Each rule consists of:

Rule ID: Unique identifier for tracking and reference

Name: Human-readable description of the detection pattern

Pattern: Regular expression or condition to match against log entries

Threshold: Number of occurrences required to trigger detection

Time Window: Duration over which threshold is evaluated

Severity: Impact level (1-10) assigned to matched events

Enabled: Flag to enable/disable the rule

## 10.7 Risk Scoring Model

The risk scoring model aggregates individual rule detections into cumulative risk scores:

Base Score = Rule Severity (1-10)

Frequency Multiplier = log2(occurrence count + 1)

Event Score = Base Score * Frequency Multiplier

Total Risk Score = Sum of all Event Scores

Risk Level = Categorized based on thresholds (Low: 0-25, Medium: 26-50, High: 51-75, Critical: 76+)

# 11. Testing and Validation Strategy

Testing and validation are conducted throughout the development lifecycle to ensure functional correctness, reliability, and alignment with project requirements.

## 11.1 Testing Levels

| Testing Level | Scope | Tools/Approach |
| --- | --- | --- |
| Unit Testing | Individual functions and methods | pytest with assertions |
| Integration Testing | Component interactions | pytest with test fixtures |
| System Testing | Complete end-to-end workflow | Manual and automated scenarios |
| Performance Testing | Processing speed and efficiency | Benchmark with 10K entries |

Table 11.1: Testing Levels

## 11.2 Test Cases by Component

### LogParser Test Cases

TC-LP-01: Parse valid syslog format file successfully

TC-LP-02: Parse valid JSON format file successfully

TC-LP-03: Parse valid CSV format file successfully

TC-LP-04: Handle malformed log entries gracefully

TC-LP-05: Handle empty files without error

TC-LP-06: Normalize timestamps across formats consistently

### RuleEngine Test Cases

TC-RE-01: Load rules from configuration file

TC-RE-02: Detect repeated failed login attempts

TC-RE-03: Detect port scanning patterns

TC-RE-04: Detect privilege escalation attempts

TC-RE-05: Handle rules with different threshold values

TC-RE-06: Enable/disable individual rules

### RiskScorer Test Cases

TC-RS-01: Calculate correct score for single detection

TC-RS-02: Aggregate scores for multiple detections

TC-RS-03: Categorize Low severity correctly (0-25)

TC-RS-04: Categorize Medium severity correctly (26-50)

TC-RS-05: Categorize High severity correctly (51-75)

TC-RS-06: Categorize Critical severity correctly (76+)

## 11.3 Validation Approach

Validation testing ensures the system meets defined requirements and user needs:

Functional Validation: Verify all FR-01 through FR-08 requirements are implemented correctly

Performance Validation: Confirm processing of 10,000 entries completes within 30 seconds

Usability Validation: Verify users can complete analysis workflow without documentation

Accuracy Validation: Test detection rules against known attack patterns in sample data

## 11.4 Test Data

Testing will use synthetic log data containing known patterns:

Normal baseline logs representing typical system activity

Failed login sequences with varying patterns and frequencies

Port scanning simulation data

Privilege escalation attempt patterns

Mixed datasets combining normal and malicious patterns

Edge cases including empty fields, unusual timestamps, and malformed entries

# 12. Conclusion

This Project Design document provides a comprehensive roadmap for the successful execution of the CyberRisk Monitor capstone project. By defining clear scope boundaries, detailed system requirements, appropriate development methodology, structured task breakdown, realistic scheduling, thorough risk management strategies, and measurable evaluation criteria, the project establishes a solid foundation for development, testing, and final delivery.

The modular architecture design ensures maintainability and supports the educational objectives of the capstone course. The rule-based detection approach provides transparency and interpretability, making the system suitable for learning cybersecurity monitoring concepts. The Agile-inspired methodology enables iterative progress with continuous feedback and adaptation.

Successful completion of this design and its associated implementation will demonstrate the team's ability to apply computer science principles in a structured, real-world context. CyberRisk Monitor serves as both a functional monitoring prototype and an educational tool, reinforcing core concepts such as log analysis, rule-based detection, and risk assessment.

This design document establishes the clear foundation required for development, testing, and final demonstration in fulfillment of the CMSC 495 capstone requirements.

# Appendix A: Detailed Class Specifications

## A.1 LogEntry Class

class LogEntry:
    """Represents a normalized log entry from any supported format."""

    Attributes:
        timestamp: datetime - When the event occurred
        source_ip: str - IP address of the event source
        dest_ip: str - IP address of the destination (if applicable)
        event_type: str - Category of the event
        user: str - Username associated with the event
        message: str - Human-readable event description
        raw_data: str - Original unparsed log line
        metadata: dict - Additional format-specific fields

    Methods:
        toDict() -> dict: Convert to dictionary representation
        fromDict(data: dict) -> LogEntry: Create from dictionary
        __str__() -> str: Human-readable string representation

## A.2 Rule Class

class Rule:
    """Represents a detection rule for identifying security patterns."""

    Attributes:
        rule_id: str - Unique identifier
        name: str - Human-readable name
        description: str - Detailed explanation
        pattern: str - Regex pattern or condition
        field: str - LogEntry field to match against
        threshold: int - Occurrences needed to trigger
        time_window: int - Seconds for threshold evaluation
        severity: int - Impact level (1-10)
        enabled: bool - Whether rule is active

    Methods:
        matches(entry: LogEntry) -> bool: Check if entry matches rule
        getSeverity() -> int: Return severity level
        enable() -> None: Activate the rule
        disable() -> None: Deactivate the rule

## A.3 Detection Class

class Detection:
    """Represents a detected security event."""

    Attributes:
        detection_id: str - Unique identifier
        rule_id: str - ID of triggering rule
        rule_name: str - Name of triggering rule
        log_entries: List[LogEntry] - Entries that triggered detection
        timestamp: datetime - When detection was generated
        score: int - Calculated risk score
        severity: str - Categorized severity level

    Methods:
        toDict() -> dict: Convert to dictionary
        getSeverity() -> str: Return severity category
        getScore() -> int: Return risk score

# Appendix B: Detection Rules Catalog

The following detection rules will be implemented in the initial release:

| Rule ID | Rule Name | Detection Pattern | Severity |
| --- | --- | --- | --- |
| RULE-001 | Brute Force Login | 5+ failed logins from same IP in 5 min | 8 |
| RULE-002 | Port Scan Detection | 10+ connection attempts to different ports | 7 |
| RULE-003 | Privilege Escalation | User gains admin/root privileges | 9 |
| RULE-004 | After-Hours Access | Login outside business hours (6PM-6AM) | 4 |
| RULE-005 | Multiple Failed SSH | 3+ failed SSH attempts in 1 min | 6 |
| RULE-006 | Suspicious File Access | Access to sensitive paths (/etc/shadow) | 8 |
| RULE-007 | Account Lockout | Account locked due to failed attempts | 5 |
| RULE-008 | New Admin Account | New account created with admin rights | 9 |
| RULE-009 | Service Stopped | Critical service stopped unexpectedly | 7 |
| RULE-010 | Unusual Data Transfer | Large outbound data transfer detected | 6 |
| RULE-011 | Multiple Source IPs | Same user logged in from 3+ IPs | 5 |

Table B.1: Detection Rules Catalog